# CVEN9723 Group Assignment

Topic: Snowy 2.0 Pumped-Hydro Project, challenges and opportunities
Group: Sample draft written as a single-author submission

## Executive summary

Snowy 2.0 is a major energy storage project that links the Tantangara and Talbingo reservoirs through long tunnels and an underground power station. It will provide around 2.2 GW of capacity to shift renewable energy from off-peak to peak times. The project has faced repeated delays, cost growth, and safety incidents. These challenges mostly come from uncertain ground conditions, complex underground works, and the need to coordinate new transmission lines. This report gives a practical overview of the project, lists the key problems, explains their causes in simple terms, and suggests basic steps to improve delivery. It also includes short comparisons to common practices and a basic risk register. The aim is to show understanding of the main issues and offer reasonable, not perfect, actions.

## 1. Project overview

Purpose. Snowy 2.0 will act like a very large battery. Water is pumped uphill when power is cheap, then released through turbines to generate during peak demand. This supports more wind and solar by balancing supply and demand.

Scope. The core works include roughly 27 km of tunnels, an underground powerhouse cavern, caverns for transformers and control equipment, access portals, and temporary work sites. Separate works build high-voltage transmission links so the power can reach the market.

Delivery structure. Snowy Hydro is the client. A joint venture handles most civil tunnelling and cavern construction. Transmission is led under separate programs. Regulators oversee safety and environmental compliance, especially because the works are in and under sensitive areas in the Snowy Mountains.

Why it matters. As older coal plants retire, the grid needs flexible capacity. Pumped hydro can provide long discharge durations compared to batteries. It can also help with system strength and stability. If Snowy 2.0 works as intended, it will support higher renewable penetration.

## 2. Key challenges

This section lists the main problems in a plain way. Later sections explain causes and what to do.

- Ground risk and tunnelling delays. The tunnel boring machine has been stopped multiple times by soft ground or very hard rock. Recovery takes time and money.

- Cost uncertainty. The original cost idea was low compared to what is now expected. Revisions keep happening.

- Schedule slippage. Early dates have moved out. Forecasts for first power and full operation were reset.

- Safety stoppages. Events like ventilation equipment failure and issues with refuge chambers have led to work halts and investigations.

- Environmental constraints. The project area includes national park land. Conditions and approvals are strict, which limits flexibility and increases oversight.

- Transmission dependency. Value depends on new lines being ready. If transmission lags, energy can be stranded.

- Industrial relations and workforce confidence. After incidents, crews may walk off or be slow to remobilise. This reduces productivity.

### Table 1. Summary of key challenges and indicative impact

| Challenge | Likely impact on cost | Likely impact on time | Notes |
| --- | --- | --- | --- |
| Uncertain ground conditions | High | High | Stops and redesigns are expensive |
| Safety incidents and compliance | Medium to High | High | Work bans halt production |
| Transmission coordination | Medium | Medium to High | Risk of stranded capacity if mis-timed |
| Environmental approvals | Medium | Medium | Limits options for rerouting |
| Industrial relations | Medium | Medium | Confidence affects productivity |

## 3. Causes

3.1 Ground and geology
The mountains have mixed rock types. Some zones are weak or fractured, and other zones are very hard and abrasive. A big tunnel boring machine moves best when conditions are predictable. When they are not, the machine slows down or stops. Restarting means extra support, grouting, or even changing the method. That adds delay and cost.

3.2 Optimism in early planning
The first public targets and cost figures were ambitious. Once works began, the reality of ground conditions and complex logistics made those targets hard to meet. This gap between optimism and actual conditions explains a lot of the cost and time movement.

3.3 Safety systems and readiness
Underground work depends on reliable ventilation, refuge chambers, alarms, and evacuation routes. If any of these are not ready, or if they fail, crews do not go underground. Regulators can shut down works until everything is compliant. Safety must be treated as core plant, not an afterthought.

3.4 Integration with transmission
The power is only useful if it can reach the grid. That requires new 330 kV or 500 kV lines and substations. If those lines are late, the powerhouse can be finished but underused. This is a planning risk that sits outside the tunnels but still affects the project outcome.

3.5 Working in a protected landscape
Approvals set limits on access, spoil placement, noise, and habitat protection. This reduces flexibility to adjust sites or routes, which makes it harder to respond to unexpected ground behaviour. It also adds reporting and audit tasks that take time.

## 4. How the problems connect

The challenges do not stand alone. The simple chains below show the links.

- Ground surprise → TBM stop → redesign and recovery → longer time → higher cost.

- Safety incident → regulator notice and work halt → low workforce confidence → slower restart → longer time.

- Late transmission → lower early revenue → pressure on financial case.

- Strict approvals → fewer options to change alignment or site layout → slower response to ground risks.

### Table 2. Causal links at a glance

| Trigger | Immediate effect | Flow-on effects |
| --- | --- | --- |
| Weak or very hard ground | Slow or stuck TBM | Extra support, changes, cost and delay |
| Ventilation failure or refuge issue | Stop-work order | Remedial works, morale drop, schedule slip |
| Approval constraints | Fewer rerouting options | Less agility when conditions change |
| Transmission schedule mismatch | Reduced dispatch | Lost revenue opportunity early on |

## 5. Stakeholders and what they want

This is a short list with simple roles. It is not exhaustive.

- Client, Snowy Hydro. Needs a deliverable project that is safe, lawful, and bankable. Also needs to communicate with government and the public.

- Civil joint venture. Needs clear scope, stable access, working safety systems, and fair risk sharing on ground conditions.

- Transmission operator. Needs corridor approvals, land access, and enough time to build lines and substations on schedule.

- Regulators. Need compliance with work health and safety and environmental conditions.

- Workforce and unions. Need safe systems, clear training, and trust in site leadership.

- Local communities and land managers. Need protection of biodiversity and amenity, control of noise and traffic, and transparent communication.

### Table 3. Stakeholder overview

| Stakeholder | Interest | Levers |
| --- | --- | --- |
| Client | Cost, time, safety, reputation | Contract settings, sequencing, reporting |
| Contractor JV | Productivity, safety, cash flow | Methods, staffing, equipment |
| Transmission program | On-time energisation | Corridor access, permits, procurement |
| Safety regulator | Zero harm, compliance | Notices, audits, approvals |
| Environmental agencies | Biodiversity and heritage | Conditions, audits, penalties |
| Communities | Amenity and trust | Consultation, mitigation, compensation |

## 6. What “good practice” looks like in context

This section is not academic. It only points to common approaches that are practical for this sort of job.

6.1 Front-load ground investigation
Do more probing ahead of the TBM in high-risk zones. Use pilot headings where possible. Set clear decision rules to switch to pre-grouting or different support if certain indicators are seen. This slows the nominal advance a little, but it reduces the chance of a long stoppage.

6.2 Treat safety as critical-path plant
Procure, install, and test ventilation and refuge systems early. Run drills before sustained excavation. Put pass-fail gates on safety systems just like gates on pressure tests or electrical commissioning. If a fan fails, the schedule will fail too, so plan them together.

6.3 Use collaborative commercial settings for ground risk
For highly variable ground, target-cost or alliance style arrangements usually work better than hard fixed price. This encourages joint problem solving instead of claim cycles. Resetting mid-project is possible, but designing collaboration from the start is better.

6.4 Plan transmission and generation together
Build a joint energisation plan with the transmission program. Include shared hold points and calendars for outages, testing, and staging. This reduces the risk that the powerhouse waits on the line or the line waits on the powerhouse.

6.5 Keep approvals current and flexible
Where the approval allows options within a defined envelope, hold those options open. For example, keep more than one spoil layout permitted, or more than one access track, so there is some room to manoeuvre if ground conditions change.

## 7. Options for the next 6 to 12 months

This is a short, realistic list. It avoids big program restructures and focuses on actions that support safe throughput.

- Expand probe drilling ahead of the TBM in identified risk bands. Log data in real time and set thresholds for pre-treatment.

- Run a safety plant sprint. Commission refuge chambers, verify ventilation readiness, and complete emergency drills before ramping up excavation.

- Create a single integrated commissioning plan that includes the underground works and the transmission energisation steps. Share it publicly.

- Publish cost and schedule ranges with uncertainty bands, not a single date. This manages expectations and reduces pressure to cut corners.

- Stabilise workforce confidence. Hold regular toolbox talks, make fixes visible, and explain rationale for any stand-downs.

- Tidy approvals. Close out any open conditions that block method changes, and lodge small modifications early if needed.

### Table 4. Simple 90-day action plan

| Action | Owner | Output |
| --- | --- | --- |
| Probe and pre-treat high-risk headings | Contractor JV, ground engineer | Lower chance of immobilisation |
| Safety plant readiness and drills | Contractor JV, regulator oversight | Fewer stoppages after incidents |
| Integrated transmission interface plan | Client with transmission operator | Joint calendar and hold points |
| Public reporting cadence | Client | Credibility with stakeholders |
| Workforce engagement | Site leadership | Better morale, steadier productivity |

## 8. Basic risk register

This is not full ISO 31000 treatment. It lists the most obvious risks, causes, and simple mitigations.

### Table 5. Top risks, simple rating

| Risk | Cause | Impact | Likelihood | Mitigation | Residual |
| --- | --- | --- | --- | --- | --- |
| TBM stuck in weak or hard ground | Variable geology | Very high time and cost | Medium | Probing, pre-grouting, backup method | Medium |
| Ventilation failure underground | Maintenance gap, wrong spec | High time, safety | Low to Medium | Early commissioning, testing regime | Low to Medium |
| Refuge chambers not ready | Procurement delay, configuration | High safety, time | Low to Medium | Treat as critical plant, acceptance tests | Low |
| Transmission not ready in time | Corridor delays | Medium revenue loss | Medium | Joint plan with shared gates | Low to Medium |
| Approvals restrict method changes | Tight conditions | Medium time | Medium | Early consultation, small mods | Low to Medium |
| Workforce walk-offs | Low trust after incidents | Medium time | Low to Medium | Visible fixes, engagement | Low |

## 9. Comparison with similar projects

- Underground rail and metro tunnels often use staged headings and probe drilling as standard. The main lesson is to spend more time before the machine reaches a risk zone. That reduces surprises.

- Hydro caverns in Europe and Asia commonly run safety drills before sustained excavation. Treating drills as a program item avoids last-minute delays.

- Target-cost contracts are common for variable subsurface works. They are not perfect, but they reduce litigated disputes and keep teams focused on throughput and safety.

These points are not special or new. They are normal practice where ground risk is high. Applying them consistently should cut the chance of long stoppages.

## 10. Short implementation outline

This is a straightforward sequence that aims to keep things moving without big redesigns.

- Confirm the ground-risk map. Use all existing data to mark the next 500 m of drive by risk class.

- For red zones, implement mandatory probe lengths and pre-treatment rules. Prepare materials and crews before arrival.

- Run a two-week safety readiness window for ventilation and refuge systems that will support the next phase of excavation.

- Hold a joint program workshop with the transmission team and set shared dates and hold points.

- Set a monthly public update with a range for key dates and a short note on what changed.

- Run two workforce briefings per week while restart ramps up. Keep them short and factual.

### Table 6. Minimal resourcing view

| Workstream | People needed | Notes |
| --- | --- | --- |
| Ground probing and pre-treatment | Shift crews, geotech engineer, grout team | Keep equipment on standby in red zones |
| Safety plant readiness | Ventilation techs, electrical, WHS officer | Include drills on roster |
| Transmission interface | Client planner, transmission planner | Use one shared action register |
| Reporting and engagement | Client comms, site leadership | Short updates with simple visuals |